## Inventory List
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
Database not working | SQL server is not started | Low | High | Developer | Start SQL server on desired port | Check before running the application
Database not accessible | Sql driver or credential is wrong | Low | High | Developer | Check the configuration and MySQL documentation | Keep the configuration backup
Github not working | Github crediantial not present | Medium | Medium | Developer | Use the github configuration to store credentials or use SSH setup | Keep the configuration backup
No project data on HDD | Accidental deletion of data | Medium | High | Developer | Use github to keep backup of code | Keep the code on Github Repo
QA Capstone Project - Bank API
Risk Assessment